## Sprint 1
Party Up Sprint 1
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE |  | Database Development and Navigation
| PartyUp | Yoan Dubuc | 2021-01-21 | 2021-02-07 | 15% | SCOPE STATEMENT |  | Planning and initial features
AT RISK | TASK NAME | FEATURE TYPE | STORY POINTS | START | FINISH | DURATION (DAYS) | Actual (Days) | STATUS | COMMENTS
| Create User Stories in Jira | Planning | 0 | 2021-01-21 | 2021-01-30 | 9 |  | In Progress
| Create issues in Jira | Planning | 0 | 2021-01-30 | 2021-01-31 | 1 |  | In Progress
| Create database | Database | 0 | 2021-02-01 | 2021-02-07 | 6 |  | In Progress
| Create Epics in Jira | Planning | 0 | 2021-01-31 | 2021-02-01 | 1 |  | In Progress
| Add logout and profile button to nav bar, add nav bar to pages | Task | 2.5 | 2021-01-28 | 2021-02-01 | 4 |  | In Progress
| Make a form to login and register | Task | 1 | 2021-01-28 | 2021-02-07 | 10 |  | In Progress
| Create a page for searching a game | Task | 2 | 2021-01-28 | 2021-02-07 | 10 |  | In Progress

## Sprint 2
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1
Feature 1
Feature 2
Feature 3
Sprint 2
Feature 4
Feature 5
Feature 6
Sprint 3
Feature 7
Feature 8
Feature 9

## Sprint 3
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1
Feature 1
Feature 2
Feature 3
Sprint 2
Feature 4
Feature 5
Feature 6
Sprint 3
Feature 7
Feature 8
Feature 9

## Backlog
Issue Type | Summary | Reporter | Priority | Story Points | Associated Epic | Sprint
Task | setup unit tests for the backend | Yoan Dubuc | Medium | - | All | All
Task | polish views and pages for the frontend | Yoan Dubuc | Medium | - | All | All
Task | add logout and profile button to nav bar, add nav bar to pages | Yoan Dubuc | Medium | 2.5 | All | 1
Task | setup some unit tests for the frontend | Yoan Dubuc | Medium | - | All | All
Task | calculate percentage matchmaking in the backend | Yoan Dubuc | Medium | 2 | Match Making, Friendships
Task | find out how to switch between pages (using react-router-dom library?) | Yoan Dubuc | Medium | 2.5 | All
Task | connect profile page frontend to backend so it updates the user | Yoan Dubuc | Medium | 2 | Match Making, Friendships
Task | add fields to user model in backend for all the questions and make function to update them | Yoan Dubuc | Medium | 3 | Match Making, Friendships, Registration
Task | Make matchmaking in the backend | Yoan Dubuc | Medium | 3 | Match Making, Friendships
Task | Create page to view all users that are matched for a particular game | Yoan Dubuc | Medium | 1 | Match Making, Friendships
Task | Connect experience level game page with backend | Yoan Dubuc | Medium | 1 | Match Making, Friendships | 2
Task | Create page to pick experience level after choosing game | Yoan Dubuc | Medium | 1 | Match Making, Friendships | 2
Task | Make function to fetch users in backend | Yoan Dubuc | Medium | 2 | Match Making, Friendships, Registration, User Authentication
Task | Handle friendships on the frontend | ward williams | Medium | 1 | Match Making, Friendships
Task | Handle friendships on the backend | ward williams | Medium | 1 | Match Making, Friendships
Task | Create page for answering questions | ward williams | Medium | - | N/A | N/A
Task | Connect frontend to backend for searching a game | ward williams | Medium | 1 | Game Search | 2
Task | Create fetching for the login and register page | ward williams | Medium | 1 | User Authentication, Registration | 2
Task | Connect to API to retrieve game information | ward williams | Medium | 3 | Game Search | 2
Task | Create page for searching a game | ward williams | Medium | 2 | Game Search | 1
Task | Create cookies for frontend | ward williams | Medium | 2.5 | All
Task | Make endpoints to make accounts in the database | ward williams | Medium | 2 | Registration, User Authentication
Task | Make a form to login and register | ward williams | Medium | 1 | Registration, User Authentication
[5 empty] | Associated User Story | 1
Epic | Game Search | Justin Ross | Medium | 7.5 | As an authenticated user, I want search for a game.As a visitor, I want to view the games that are supported in the app.
Epic | Registration | ward williams | Medium | 5 | As an authenticated user, I want to edit/modify my account information
Epic | Friendships | ward williams | Medium | 9 | As an authenticated user, I want accept and decline matches
Epic | Match Making | ward williams | Medium | 9 | As an authenticated user, I want to generate matches
Epic | User Authentication | ward williams | Medium | 5 | As an authenticated user, I want to edit/modify my account information
Story | As a visitor, I want to view the games that are supported in the app. | ward williams | Medium | 2
Story | As an authenticated user, I want to edit/modify my account information | ward williams | Medium | 10
Story | As an authenticated user, I want accept and decline matches | ward williams | Medium | 9
Story | As an authenticated user, I want to generate matches | ward williams | Medium | 9
Story | As an authenticated user, I want search for a game. | ward williams | Medium | 5.5
Database | Create database | Ward Williams | High | -
Planning | Create User Stories | Ward Williams | High | -
Planning | Create epics from user stories | Ward Williams | High | -
Planning | Create Jira board | Ward Williams | High | -
Planning | Create issues from epics/user stories | Ward Williams | High | -